## PO Details
Oracle Code | Description | Qty | PO
NET005954 | Services for increase in Height of 1 RRU | 20 | BAL OR/115/32749
NET005935 | Services for Increase in height of Additional Incremental RRU | 40 | BAL OR/115/32749
NET005946 | Services for Increase in height of 1 Antenna | 20 | BAL OR/115/32749
NET005947 | Services for Increase in height of additional Incremental Antenna | 100 | BAL OR/115/32749

## 20 Sites
Site ID | Tech | Town | District | Site Name | DoA | Site Type | Baseband | Site Tagging | Tower Type | Sectors | No. of sectors Ht Increment required | Tower Ht | Pre GSM Azimuth | Pre GSM Height | No. of Antennas | Ht Increment Requirement | Post GSM Azimuth | Post GSM Height | Priority | ToCo Name | ToCo ID | SR No. | New SR for INDUS | SR Date | Month Target | Timeline | Ht Increment Status | Field Input
ORMTP-01 | 2G/L1800/L2100/L900/L2300 | MITRAPUR | BALASORE | EORMTP01 | 2008-02-16 | SRAN | Airscale | RURAL | GBT | 4th sector | 1 | 50 | 60_220_315 | 40_40_45_40 | 1_1_1_1 | 0/0/0/5 | 60_220_315 | 40_40_45_45 | Critical | INDUS/INFRATEL | ORGT11548 | SR1251780 | - | 2021-06-24
OR2248 | 2G/L1800/L900 | NAMPO | BALASORE | EOR2248 | 2009-08-20 | SRAN | Flexi Multiradio | RURAL | GBT | 1st 2nd and 3rd sector | 3 | 40 | 70_190_300 | 29_29_29 | 1_2_2 | 6/6/6 | 70_190_300 | 35_35_35 | Critical | CNIL | ORNAM001 | 53796 | - | 2021-07-08
OR2141-02 | 2G/L1800/L900/L2300 | OSHALA | JAJPUR | EOR214102 | 2013-12-26 | SRAN | Flexi Multiradio | RURAL | GBT | 1st 2nd 3rd and 4th sector | 4 | 50 | 50_120_220_280 | 33_33_38_38 | 2_2_2_2 | 12/12/7/7 | 50_120_220_280 | 45_45_45_45 | P0 | ATC | ORIJAJ1075 | 53733 | - | 2021-07-01
ORBOA-01 | 2G/L1800/L900/L2300 | BONAIGARH | SUNDARGARH | EORBOA01 | 2008-02-06 | SRAN | Airscale | RURAL | GBT | 3rd sector | 1 | 50 | 320_90_130_220 | 25_40_40_40 | 2_2_2_2 | 0/0/5/0 | 320_90_130_220 | 25_40_45_40 | P1 | INDUS/INFRATEL | ORGT11480 | SR1251764 | - | 2021-06-24
ORTAL-11 | 2G/L1800/L900/L2300 | TALCHER | ANGUL | EORTAL11 | 2008-12-05 | SRAN | Flexi Multiradio | NEXT 30 TOWN | GBT | 1st and 2nd sector | 2 | 40 | 15_150_275 | 30_20_35 | 1_1_1 | 5/15/0 | 15_150_275 | 35_35_35 | Critical | INDUS/INFRATEL | ORGT12235 | Airtel/R/RL-151 | R/RL-4887650 | 2021-07-08
ORBHU-15 | L1800/L2100/L2300 | PATIA | KHURDA | EORBHU15 | 2004-12-16 | SRAN | Flexi Multiradio | TOP 5 | GBT | 1st 2nd and 3rd 4th sector | 4 | 40 | 340_50_260 | 20_30_20_- | 1_2_2 |  | 340_50_260 | 38_38_38_38 | Critical | INDUS | IN-2035336 | - | R/RL-4967574 | 2021-08-16
ORJPR-51 | 2G/L1800/L900/L2300 | JAJPURROAD | JAJPUR | EORJPR51 | 2018-07-21 | SRAN | Flexi Multiradio | RURAL | GBT | 3rd sector | 1 | 40 | 0_155_280 | 29_29_29 | 2_2_2 | 0/0/9 | 0_155_280 | 29_29_38 | P0 | ATC | ORIJAJ1381 | 53963 | - | 2021-08-21
ORBHU-272 | 2G/L1800/L2100/L900/L2300 | BHUBANESWAR | KHURDA | EORBHU272 | 2015-11-27 | SRAN | Airscale | TOP 5 | GBT | 1st and 3rd sector | 2 | 40 | 90_210_290 | 25_35_25 | 2_2_2 | 10/0/10 | 90_210_290 | 35_35_35 | P2 | ATC | OR3021 | 54209 | - | 2021-09-20
ORBHU-119 | 2G/L1800/L2100/L900/L2300 | BHUBANESWAR | KHURDA | EORBHU119 | 2009-01-14 | SRAN | Flexi Multiradio | TOP 5 | GBT | 1st and 2nd sector | 2 | 40 | 20_110_200 | 22_25_35 | 2_2_2 | 13/10/0 | 20_110_200 | 35_35_35 | P2 | INDUS/INFRATEL | IN-2037474 | - | R/RL-5026336 | 2021-09-20
ORKEN-05 | 2G/L1800/L2100/L900/L2300 | KENDRAPARA | KENDRAPADA | EORKEN05 | 2007-02-23 | SRAN | Airscale | NEXT 30 TOWN | GBT | 2nd Sec | 1 | 30 | 130_230_320 | 29_21_27 | 2_2_1 | 0/8/0 | 130_230_320 | 29_29_27 | Critical | INDUS | IN-2036064 | - | R/RL-5046610 | 2021-10-01
ORKRG-01 | 2G/L1800/L2100/L900/L2300 | KALUPADAGHAT | KHURDA | EORKRG01 | 2007-01-31 | SRAN | Airscale | RURAL | GBT | 1st 3rd and 4th sector | 3 | 40 | 70_140_240_340 | 30_35_30_30 | 2_2_2_2 | 8/0/8/8 | 70_140_240_340 | 38_35_38_38 | Critical | INDUS/INFRATEL | ORGT10859 | - | R/RL-5055764 | 2021-10-08
ORCKL-01 | 2G/L1800/L900/L2300 | CHIKLAHANDI | GANJAM | EORCKL01 | 2006-06-30 | SRAN | Airscale | RURAL | GBT | 2nd and 3rd sector | 2 | 40 | 50_190_230 | 30_30_30 | 2_2_2 | 0/8/8 | 50_190_230 | 30_38_38 | Critical | INDUS/INFRATEL | ORGT10568 | - | R/RL-5110188 | 2021-11-16
ORCOR-03 | 2G/L1800/L900/L2300 | CHHORIAGARH | KALAHANDI | EORCOR03 | 2011-01-24 | SRAN | Flexi Multiradio | RURAL | GBT | 1st sector | 1 | 50 | 80_190_285 | 40_45_38 | 1_1_1 | 5/0/0 | 80_190_285 | 45_45_38 | Critical | INDUS/INFRATEL | ORGT17324 | - | R/RL-5110193 | 2021-11-16
ORDRT-01 | 2G/L1800/L900/L2300 | DUDURANTA | JAJPUR | EORDRT01 | 2006-12-23 | SRAN | Flexi Multiradio | RURAL | GBT | 1st 2nd and 3rd Sector | 3 | 40 | 50_120_250 | 35_35_30 | 2_2_2 | 4/4/9 | 50_120_250 | 39_39_39 | Critical | Bharti Infratel | ORGT10807 | - | R/RL-5152733 | 2021-12-13
ORBAC-05 | 2G/L1800/L2100/L900/L2300 | BALICHANDRAPUR | CUTTACK | EORBAC05 | 2008-08-05 | SRAN | Flexi Multiradio | RURAL | GBT | 4th sector | 1 | 50 | 60_160_340_280 | 35_40_35_35 | 2_2_2 | 0/0/0/10 | 60_160_340_280 | 35_40_35_45 | Critical | Bharti Infratel | ORGT11927 | - | R/RL-5152943 | 2021-12-13
ORJHU-08 | 2G/L1800/L900/L2300 | JHARSUGUDA | JHARSUGUDA | EORJHU08 | 2008-11-22 | SRAN | Airscale | NEXT 30 TOWN | GBT | 2nd and 3rd Sector | 2 | 40 | 10_110_220_280 | 38_28_22_38 | 2_1_1_1 | 0/10/16/0 | 10_110_220_280 | 38_38_38_38 | Critical | Bharti Infratel | ORGT12218 | - | R/RL-5152953 | 2021-12-13
ORLKP-01 | 2G/L1800/L2100/L900/L2300 | LAKHANPURROAD | JHARSUGUDA | EORLKP01 | 2005-12-25 | SRAN | Airscale | RURAL | GBT | 1st and 2nd Sector | 2 | 70 | 130_330_250_80 | 30_37_30_42 | 1_1_1_1 | 12/5/0/0 | 130_330_250_80 | 42_42_30_42 | Critical | Bharti Infratel | ORGT10338 | - | R/RL-5152960 | 2021-12-13
ORPDR-01 | 2G/L1800/L900/L2300 | PANDARA | JAGATSINGHPUR | EORPDR01 | 2008-03-31 | SRAN | Flexi Multiradio | RURAL | GBT | 1st and 2nd Sector | 2 | 50 | 80_160_280_0 | 30_30_40_38 | 1_1_1_1 | 10/10/0/0 | 80_160_280_0 | 40_40_40_38 | Critical | Bharti Infratel | ORGT11642 | - | R/RL-5152964 | 2021-12-13
ORSRN-01 | 2G/L1800/L900/L2300 | SANDARA | JAGATSINGHPUR | EORSRN01 | 2008-03-31 | SRAN | Flexi Multiradio | RURAL | GBT | 2nd sector | 1 | 50 | 20_140_240 | 30_35_35 | 1_1_1 | 0/10/0 | 20_140_240 | 30_45_35 | Critical | Bharti Infratel | ORGT11672 | - | R/RL-5152979 | 2021-12-13
ORBHO-01 | 2G/L1800/L900/L2300 | BHATLAIDA | JHARSUGUDA | EORBHO01 | 2012-06-22 | SRAN | Flexi Multiradio | RURAL | GBT | 1st 2nd and 3rd Sector | 3 | 60 | 30_140_300 | 38_38_38 | 1_1_1 | 12/12/12 | 30_140_300 | 50_50_50 | Critical | ATC | OR1072 | 54776 | - | 2021-12-17